## Extension
Section 8's open directions: |  |  | Integrating the count methodology into a wider framework for outstanding claims amount - potentially merged with RBNS predictions methods (Crevecoeur, Robben & Antonio (2022)/Lopez & Milhaud) (2021)
Extending beyond point predicitions toward quantifying uncertainty
RBNS/severity requires claims amounts
Unvertainty quantification run on the simlated pipeline, is evaluable, makes the measure theory chapter load-bearing, has clean benchmark waiting
Paper computes CRPS, but on the individual reporting_dealy survival function - not on the predictive distribution of the aggregate reserve. Nobody yet has scored the reserve distribution in the framework
Three components for the extension - decreasing order of theoretical interest & increasing order of implementation ease:
Estimation variance for COX via the martingale route
Information matrix from the tied partial likelihood -> Var(\theta^)
Martingale-base variance for the baseline
Delta method to get development-factor standard errors
Propagate through the product to the reserve
The original derivation comes straight out of Theory layer 2 & 4
Bootstrap for XGB
With hyperparameters frozen from a single tuning run
Non-negotiable simplication
Paper reports NN fits at 100-200 minutes
Bootstrapping NN is arithmetically impossible
|  | Decide now to drop NN from the UQ part entirely and say so in the thesis with computational-cost justification |  | WHY?
Defensible choice - not a weakness
Process variance
Poisson/thinning model for lower-triangle counts given the develpment factors
Giving a full predictive distribution rather than just parameter unvertainty
All evaluated by empirical coverage of nominal 95% intervals across the 20 replicates per scenario plus interval width, reserve-level CRPS
Compare to Mack

## Timeline
Assuming 20-22 hours/week
Bachelor Timeline
Block | Dates | Theory | Pipeline | Extension | Gate
1 | Sep 8 - Sep 27 | Read to a target | ReSurv installed
|  | Write the chapter skeleton | Secnario Alpha reporduced end-to-end
|  | (bare statements of the five results inteded to prove) | Time the fits
Read only to fill them
Williams Ch.9-12 for conditional expectation and martingales
(faster than Schilling)
Schilling for measure-space vocabulary only
2 | Sep 28 - Oct 18 | ABGK Ch. II | All six scenarios running | Bootstap loop working on COX only
|  | (counting processes, Doob-Meyer, stochastic integrals, martingale CLT, product integration) | Chain-ladder & Mack benchmarks in place | One scenario
|  | Draft Layer 1-2 |  | Proof of concept
3 | Oct 19 - Nov 15 | ABGK Ch. III | Oct 19: Data gate | Oct 19: extension locked | One-page extension spec written
|  | (truncation/censoring conditions) | Core benchmark table complete on simulated data | Derive COX variance | Which uncertainty, which estimator, which benchmark
|  | Layer 3 reverse-time argument drafted |  | Implement delta method | If can't write that page, the extension isn't ready
|  | Ch. VII for Cox asymptotics |  | XGB bootstrap running
Layer 4
4 | Nov 16 - Dec 4 | Layer 5 | Real ERGO data folded in | Coverage study across all scenarios | If UQ isn't running end-to-end by then:
|  | (product integrals) |  | Dec 4: results freeze | drop to COX-only asymptotic intervals on two scenarios
Full theory chapter in draft
5 | Dec 5 - Dec 18 | Introduction |  | Extension results written up
|  | Litteratur |  | Dec 18: full draft to Munir
|  | Discussion - written last |  | RBNS as a written discussion section only
6 | Dec 19 - Jan 15 | Revision on Munir's comments |  | One or two pages sketching how the severity extension would attach
|  | Holiday buffer |  | No code